## Blank Weekly Sheet
Zeitplan - Gantt Diagramm - Wöchentlich
 | time axis 2015-09-07 to 2016-01-13
2015-09-07 | bar: 2015-09-07 to 2015-10-28
|  |  | ISO WOCHEN NUM | W37 | W38 | W39 | W40 | W41 | W42 | W43 | W44 | W45 | W46 | W47 | W48 | W49 | W50 | W51 | W52 | W53 | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36
|  |  | Monat | W37: SEP; W41: OCT; W45: NOV; W50: DEC; W1: JAN; W5: FEB; W10: MAR; W14: APR; W18: MAY; W23: JUN; W27: JUL; W31: AUG; W36: SEP
|  |  | Montag | 2015-09-07 | 2015-09-14 | 2015-09-21 | 2015-09-28 | 2015-10-05 | 2015-10-12 | 2015-10-19 | 2015-10-26 | 2015-11-02 | 2015-11-09 | 2015-11-16 | 2015-11-23 | 2015-11-30 | 2015-12-07 | 2015-12-14 | 2015-12-21 | 2015-12-28 | 2016-01-04 | 2016-01-11 | 2016-01-18 | 2016-01-25 | 2016-02-01 | 2016-02-08 | 2016-02-15 | 2016-02-22 | 2016-02-29 | 2016-03-07 | 2016-03-14 | 2016-03-21 | 2016-03-28 | 2016-04-04 | 2016-04-11 | 2016-04-18 | 2016-04-25 | 2016-05-02 | 2016-05-09 | 2016-05-16 | 2016-05-23 | 2016-05-30 | 2016-06-06 | 2016-06-13 | 2016-06-20 | 2016-06-27 | 2016-07-04 | 2016-07-11 | 2016-07-18 | 2016-07-25 | 2016-08-01 | 2016-08-08 | 2016-08-15 | 2016-08-22 | 2016-08-29 | 2016-09-05
Kickoff | bar: W37
Ende Elaboration
Analyse
Ausgangslage | bar: W38
Infrastruktur aufsetzen | bar: W38
Meilensteine | bar: W38
Use Cases | bar: W38
Anforderungspezifikation | bar: W38 to W39
Testspezifikation | bar: W39
Domainanalyse | bar: W39
Projektmanagement
Arbeitspakete | bar: W39
Projektplan | bar: W39
Risikomanagement | bar: W39
Architekturprototyp
Design
Guidelines definieren | bar: W40
Architektur | bar: W40
Evaluation Libraries | bar: W40
Nebenläufigkeitskonzept | bar: W40
Architekturprototyp | bar: W40 to W41
UI Designstudie | bar: W41
Zwischenpräsentation
Implementation
Iteration 0 | bar: W42
Iteration 1 | bar: W43
Iteration 2 | bar: W44
Dokumentation
Zwischenpräsentation | bar: W44
Feature 75% | bar: W45
Implementation
Iteration 3 | bar: W45
Produkt fertig
Implementation
Iteration 4 | bar: W46
Iteration 5 | bar: W47
Ende Testphase
Testing
Bugfixes 0 | bar: W48
Testtag bei Fluxron | bar: W48
Bugfixes 1 | bar: W49
Abgabe Abstract
Dokumentation
Benutzerhandbuch | bar: W50
Abstract | bar: W50
Abgabe Bericht
Dokumentation
Bericht | bar: W51
Schlusspräsentation | bar: W51

## Date Formatting Strings
LOCAL SPECIFIC DATE STRINGS
Having trouble displaying dates correctly?
Excel's Text() function, which is used extensively to auto-format the spreadsheet, uses "text format strings" to translate
a date into other representations. However, these text format strings are locale-dependent. For example, in the USA
the function Text(A1,"MMM") will return the three-letter month acronym (e.g. "MAR" for March) for a date value.
To get around this problem without writing macros, I'm storing the format strings here for use in the main worksheet.
When you change these values, the "Blank Sheet" and "Example Sheets" will update.
three day month | mmm | change to your locale string (see your Excel documentation for Text() function and dates)
For example, in Turkish, the appropriate strings are:
three day month | mmm
Thanks to Mehmet CAN, a management consultant based in Turkey, for tracking down this issue and providing the solution.
Additonal references:
http://www.rondebruin.nl/international.htm
http://www.excelbanter.com/showthread.php?t=230221

## Example Weekly Sheet
SAMPLE WEEKLY SHEET
edit this year v | time axis 1905-07-03 to 1905-11-08
2011 | bar: 1905-07-03 to 1905-08-23
|  |  | ISO WEEK NUM | W52 | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40 | W41 | W42 | W43 | W44 | W45 | W46 | W47 | W48 | W49 | W50 | W51 | W52
|  |  | MONTH | W52: DEC; W1: JAN; W6: FEB; W10: MAR; W14: APR; W18: MAY; W23: JUN; W27: JUL; W31: AUG; W36: SEP; W40: OCT; W45: NOV; W49: DEC
|  |  | (MON)DAY | 2010-12-27 | 2011-01-03 | 2011-01-10 | 2011-01-17 | 2011-01-24 | 2011-01-31 | 2011-02-07 | 2011-02-14 | 2011-02-21 | 2011-02-28 | 2011-03-07 | 2011-03-14 | 2011-03-21 | 2011-03-28 | 2011-04-04 | 2011-04-11 | 2011-04-18 | 2011-04-25 | 2011-05-02 | 2011-05-09 | 2011-05-16 | 2011-05-23 | 2011-05-30 | 2011-06-06 | 2011-06-13 | 2011-06-20 | 2011-06-27 | 2011-07-04 | 2011-07-11 | 2011-07-18 | 2011-07-25 | 2011-08-01 | 2011-08-08 | 2011-08-15 | 2011-08-22 | 2011-08-29 | 2011-09-05 | 2011-09-12 | 2011-09-19 | 2011-09-26 | 2011-10-03 | 2011-10-10 | 2011-10-17 | 2011-10-24 | 2011-10-31 | 2011-11-07 | 2011-11-14 | 2011-11-21 | 2011-11-28 | 2011-12-05 | 2011-12-12 | 2011-12-19 | 2011-12-26
CLIENT INTERACTION |  |  |  | W1: C1; W6: C2; W13: C3
| C1 - Requirement Handoff |  |  | W1: C1 provide to engineering
| C2 - Approval |  |  | W5: S1 review
C3 - Signoff Work Complete
PLAYER APPLICATION (Joe) |  |  |  | W1: C1; W5: P1; W10: P2
| P1 - engineering prototype |  |  | W1: C1 required to start
| P2 - styled prototype |  |  | W5: S1 review
dependency on Frida-S2
PLAYER ARTWORK (Frida) | bar: W3 to W7
| S1 - skin design |  |  | W5: S1 delivery; W7: S2 delivery
approval by client
S2 - skin delivery
S3 - 25% client fixups
< select this entire row, right-click to insert more space